## Sheet1
Task | Start Date | Duration (days)
Project Backbone Design | 2021-03-17 | 2
User Interface Design | 2021-03-19 | 6
Concept Presentation | 2021-03-25 | 7
Progress Reivew | 2021-07-07 | 7
Minimum Viable Product | 2021-04-09 | 0
System Design Documentation | 2021-12-04 | 0
Progress Reivew | 2021-12-18
Project Changes | 2021-12-29 | 0
Final Project Testing | 2021-01-28 | 0
Final Project Documentation | 2021-02-07 | 3
Final System Testing | 2021-04-30 | 1

## Sheet2
Task ID | Task Description | Task Duration | Start Date | End Date | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01
1 | Project Backbone Design | 2 | 2021-03-17 | 2021-03-19 | X | X | X
2 | User Interface Design | 6 | 2021-03-19 | 2021-03-25 |  |  | X | X | X | X | X | X | X
3 | Backend Implementation | 7 | 2021-03-25 | 2021-04-01 | [8 empty] | X | X | X | X | X | X | X | X
4 | API intergrations | 7 | 2021-04-01 | 2021-04-08 | [15 empty] | X | X | X | X | X | X | X | X
5 | MVP Presentation | 1 | 2021-04-08 | 2021-04-09 | [22 empty] | X | X
6 | User Interface Re-design/Additions | 3 | 2021-04-09 | 2021-04-12 | [23 empty] | X | X | X | X
7 | Backend Implementation changes | 5 | 2021-04-12 | 2021-04-17 | [26 empty] | X | X | X | X | X | X
8 | First Final System Implementation | 7 | 2021-04-17 | 2021-04-24 | [31 empty] | X | X | X | X | X | X | X | X
9 | Troubleshooting | 5 | 2021-04-24 | 2021-04-29 | [38 empty] | X | X | X | X | X | X
10 | Final System Implementation | 1 | 2021-04-29 | 2021-04-30 | [43 empty] | X | X
| START DATE | 2021-03-17
| END DATE | 2021-04-30
| PROJECT DURATION (Days) | 44